## Sheet1
Company Name | PO No. | Date of PO | Actual Date of Supply from PO | Supply Date | Supply Delay date | Payment Receipt date | Delay in receiving payment | Location | State | Client Responses | RAAS Responses | Contact Person Name | Address | Contact No. | PBG | Comments | Ravindra- 8879667349 BD | PBG Date
IOCL | 27185098 | 2021-08-26 | 2021-12-26 | 2021-11-06 |  | 2022-02-08 | 94 | M/s Jashandeep Cyber Fuels IndianOil Petrol Pump Tafazalpura Patiala 147003 Field Officer : 9988651969 Dealer : 8146411147 | Punjab |  |  | Dwarika Prasad | Sangrur Divisional Office, IOCL, Elwal Road, near Aishwan Beed, Sangrur, Punjab 148001 | 9769064952 | Yes | Delivered to client- POI on leave this week | Ankit Kumar- 9418038088 | Despite submitting
| 27185162 | 2021-08-26 | 2021-12-26 | 2021-11-06 |  | 2022-02-08 | 94 | Address : M/s J.P Filling Station, IndianOil Petrol Pump Samana, Patiala 147101 Dealer: 9888742286 Field Officer: 9417217142 | Punjab |  |  | Dwarika Prasad |  | 9769064952 | Yes | Delivered to client- POI on leave this week
| 27203816 | 2021-09-06 | 2022-01-06 | 2021-11-09 |  | 2022-02-08 | 97 | Address : Kamat Brothers, NH-4, Shiroli Naka, Maharashtra, PIN - 416122 Dealer Contact – Sh. Kamat – Mob - 9822047577 | Maharashtra |  |  | Jagdish Sona |  | 9426416044 | No | Pending from Bank for issuance | Amit Jaiswal- 9322909035
| 27276739 | 2021-10-08 | 2022-02-08 | 2021-11-13 |  | 2022-02-04 | 83 | M/s Sushmitha Filling Station, NDIAN OIL DEALERS MADHURAWADA ANDHRA PRADESH.PIN 530041 Dealer Contact – 9949288898 | Andhra Pradesh |  |  | Vanaparthi |  | 6360183837 | Yes | OK- Concern person out of station, will release the BG amount next week
| 27187114 | 2021-08-27 | 2021-12-27 | 2021-11-16 |  | 2022-02-09 | 85 | Indian Oil Corporation Ltd, M/s COCO RO Bijapur, NH 13, Bijapur Bypass, Bijapur District , Karnataka , 586104 Contact Person : Ashwani Singh- 9752593835 | Karnataka |  |  | Ashwani Singh Baghel |  | 9752593835, | Yes | New BG required in security deposit format, we have denied
| 27710611 | 2022-04-02 | 2022-08-02 | 2022-05-28 |  | 2022-10-12 | 137 | M/s Saraswati Filling Centre,Basti Bypass District - Basti PIN- 272001 | UTTAR PRADESH |  |  | Akash Deep/ Mod. Aquil |  | 9415670321 / 7417264926 | Yes | OK- BG confirmation from client side sent to bank
| 27710611 | 2022-04-02 | 2022-08-02 | 2022-05-28 |  | 2022-10-12 | 137 | RKBK LIMITED GANDHI NAGAR District BASTI PIN- 272001 | UTTAR PRADESH |  |  | Akash Deep/ Mod. Aquil |  | 9415670321 / 7417264926 | Yes | OK- BG confirmation from client side sent to bank
| 27710611 | 2022-04-02 | 2022-08-02 | 2022-05-30 |  | 2022-10-12 | 139 | OM AUTOMOBILES, BHITTI RAWAT ON NH-28 DISTT- GORAKHPUR PIN- 273209 | UTTAR PRADESH |  |  | Akash Deep/ Mod. Aquil |  | 9415670321 / 7417264926 | Yes | OK- BG confirmation from client side sent to bank
| 27710611 | 2022-04-02 | 2022-08-02 | 2022-05-30 |  | 2022-10-12 | 139 | VINDHYAWASINI AUTOMOBILES DEORIA BYPASS ROAD DIST.GORAKHPUR PIN-273016 | UTTAR PRADESH |  |  | Akash Deep/ Mod. Aquil |  | 9415670321 / 7417264926 | Yes | OK- BG confirmation from client side sent to bank
| 27847249 | 2022-05-23 | 2022-09-23 | 2022-07-18 |  | 2022-10-19 | 93 | M/s Undre Patil Petroleum, Village Sanaswadi, Pune - 412208 | Maharashtra |  |  | Shailendra Agrawal |  | 9417800882 | No | Pending from Bank for issuance
| 27846712 | 2022-05-23 | 2022-09-23 | 2022-08-26 |  | 2022-10-21 | 56 | M/s Tibetan CO-OP STY LTD, Indian oil dealers , Gollarhosalli Po bylakuppepriya patna,Mysore -571104 | Karnataka |  |  | Ashwani Singh Baghel |  | 9752593835 | No | Pending with client- will confirm with finance and revert back tomorrow
| 27846712 | 2022-05-23 | 2022-09-23 | 2022-09-14 |  | 2022-10-19 | 35 | M/S. Shree Mulsiddeshwara Petroleum IOCL Siddapur,Taluka, KARNATKA. | Karnataka |  |  | Ashwani Singh Baghel |  | 9752593835 | No | Pending with client- will confirm with finance and revert back tomorrow
| 27846712 | 2022-05-23 | 2022-09-23 | 2022-11-30 | 68 | 2023-01-13 | 44 | M/s. SHRI LAKSHMIDEVI HIGHWAY S.S. INDIAN OIL DEALERS, SY. NO.200/9 KANAGALA TQ. HUKKERI, 591225,BELGAUM | Karnataka |  |  | Ashwani Singh Baghel |  | 9752593835 | No | Pending with client- will confirm with finance and revert back tomorrow
| 27770977 | 2022-04-25 | 2022-08-25 | 2022-12-02 | 99 | 2023-02-09 | 69 | M/s Uday Fuel Services,Village Tathawade, Taluka Mulshi,Dist Pune under Pune Divisional Office 411001 | Maharashtra |  |  | Shailendra Agrawal |  | 9417800882 | No | Pending from Bank for issuance
| 27743760 | 2022-04-13 | 2022-08-13 | 2022-12-27 | 136 | 2023-03-28 | 91 | Vikas filling station- INDION OIL DEALER DHENSA NAUGARH SIDHARTHANAGAR DISTT., 272208 | UTTAR PRADESH |  |  | Akash Deep/ Mod. Aquil |  | 9415670321 / 7417264926 | Yes | OK- BG confirmation from client side sent to bank
| 27743760 | 2022-04-13 | 2022-08-13 | 2022-12-31 | 140 | 2023-03-28 | 87 | Bajrangbali Awadesh Filling Station - VILL KANWALPUR ( VIKRAMJOT ) PO BHELWA BAGNALA BASTI DISTT- BASTI- 272129 CONTACT NO.- 9935069196 | UTTAR PRADESH |  |  | Akash Deep/ Mod. Aquil |  | 9415670321 / 7417264926 | Yes | OK- BG confirmation from client side sent to bank
| 27710611 | 2022-04-02 | 2022-08-02 | 2022-12-31 | 151 | 2023-03-28 | 87 | Sonbarsa Automobiles- INDIAN OIL DEALER NH-28 VILL. SONBARSA DISTT.- GORAKHPUR Pin-273002 contact No.-9935422221 | UTTAR PRADESH |  |  | Akash Deep/ Mod. Aquil |  | 9415670321 / 7417264926 | Yes | OK- BG confirmation from client side sent to bank
| 27847249 | 2022-05-23 | 2022-09-23 | 2023-01-13 | 112 | 2023-02-15 | 33 | M/s Narayan Maharaj, DEULGAON GADA ON CHAUFULLAH SUPE RO GAT NO.625 (P) DEULGAON GADA(V) DAUND (T) 413801 | Maharashtra |  |  | Shailendra Agrawal |  | 9417800882 | No | Pending from Bank for issuance
| 27833252 | 2022-05-18 | 2022-09-18 | 2023-01-21 | 125 | 2023-03-06 | 44 | M/s. GOPAL'S OIL CO. VILLAGE BIR KAULI NH-07 (OLD NH-64)Between 37-41 kms, PATIALA, Punjab, Pin Code : 140701 : 9878609221/ 9878609221 | Punjab |  |  | Dwarika Prasad |  | 9769064952 | No | BG collection from bank pending
| 27710611 | 2022-04-02 | 2022-08-02 | 2023-01-31 | 182 |  |  | BARANAGAR AUTOMOBILES- INDIANOIL DEALER SH-72GOLA BAZAR LOCK NO 14015 DIST.GORAKHPUR DISTT.- GORAKHPUR Pin- 273408 CONTACT NO.- 9415210766 | UTTAR PRADESH | Payment regarding supply sent to finance and it is in process | 15 April SES Received- 41939340, sent on 17 | Akash Deep (SO)/ Mod. Aquil (DO) |  | 9415670321 / 7417264926 | Yes | OK- BG confirmation from client side sent to bank |  | 2023-04-17
| 27710611 | 2022-04-02 | 2022-08-02 | 2023-02-03 | 185 |  |  | NEW BHARAT TRANSPORT COMPANY- BANDHYA KHURD NH 28 KUSHINAGAR. DISTT- KUSHINAGAR PIN CODE 274702 - 9415320473 | UTTAR PRADESH | Payment regarding supply sent to finance and it is in process | 16 April SES Received- 41939340, sent on 17 | Akash Deep (SO)/ Mod. Aquil (DO) | UPSO-I State Office, Indian Oil Bhawan, TC 39-V, Vibhuti Khand, Gomti Nagar, Lucknow, Uttar Pradesh 226010 | 9415670321 / 7417264926 | Yes | OK- BG confirmation from client side sent to bank |  | 2023-04-17
| 27743760 | 2022-04-13 | 2022-08-13 | 2023-02-20 | 191 |  |  | Gautam Buddha Auto Services, Indian Oil Retail Outlet, Village – Birdpur, Distt - Siddharthnagar, Pin Code - 272202 (Invoice No. RAAS/P5/2223/18 and RAAS/P5C/2223/32) | UTTAR PRADESH | No communication | Not Received | Akash Deep (SO)/ Mod. Aquil (DO) |  | 9415670321 / 7417264926 | Yes | OK- BG confirmation from client side sent to bank |  | 2023-04-20
| 27860118 | 2022-05-27 | 2022-09-27 | 2023-02-28 | 154 |  |  | M/S BHANSALI FUELS (SAP Code- 178525) NH-6, RHS, RAIPUR-SAMBALPUR ROAD, ARANG ROAD, VILLAGE-CHEDI KHEDI, RAIPUR, CG PIN -492101. No- 9302940004 | Chhattisgarh |  |  | Balkrishna Verma |  | 8805026944 | No | Pending for confirmation from client side to make BG 10L, PO 50L
Payment for supply not received
| SES | Service Entry Sheet
Indicate Liquidity Damages
Indicate Late Delivery
10% of supply amount holdup due to non-comissioning
PBG Payment not received
PB | Dwarika Prasad Divisional Ofc | BG/SD- 6,01,076
MH | Jagdish Sona Divisional Ofc | O&M- 2,02,358 | Ashmita Paul (State Office) | BG/SD- 15,71,612 | BG not sent from us | GST
UP | Akashdeep SO |  | 10 location |  |  | RAAS/P5/2223/12 | 2022-12-31 | 882000
|  |  | 27743760*3, 27710611*7 |  |  | RAAS/P5/2223/13 | 2022-12-31 | 882000 | Issue from our side
| 10% hold against transportation | Transportation | Supply |  | BG | RAAS/P5/2223/16 | 2023-01-31 | 882000 | Not received
| RAAS/P5C/2223/22 |  |  |  |  | RAAS/P5/2223/17 | 2023-02-03 | 882000
| RAAS/P5C/2223/23 |  |  |  |  | RAAS/P5C/2223/23 | 2022-12-31 | 18306
| RAAS/P5C/2223/24 |  |  |  |  | RAAS/P5C/2223/24 | 2022-12-31 | 20169
[6 empty] | RAAS/P5C/2223/28 | 2023-01-31 | 20399
[6 empty] | RAAS/P5C/2223/29 | 2023-02-03 | 21222
Total | 38249 | 135405 | 5782000 |  | 1544394 |  |  | 3608096
T+S | 5917405
GST | 3608096
BG | 1544394
Hold | 38249
Receivable | 11108144
KASO | Vasanth Kannan- 7338313344, Sunitha- | SD (Total Package) | 10% Holding | Invoice | Status
Sumitha | New format for 3 package fillup sent, confirmation pending | 308167 | 1068200 | 377900 | Client has sent letter to bank and scan copy of letter to us, Janak has to followup with bank regarding the same. Bank will close the BG and issue a new one.
4 Packages | 1 package payment clear
1 Package | Post warranty BG to be sent | E&C 147500 | 490000 | 36136 | Vikas Abushi, Lakshmidevi Highway
Tibetian | Comission pending, Vasant Kannan
TAPSO | Prashant Vannaparthi
1 Pacakge | BB from bank within 2 days | 153150 | - | 347195
Invoice | Mail sent for invoice process
MSO | Shailendra, 9417800882
4 Packages | 1 comissioned, 3 remaining |  | 1734600 | 220427 | 2 site comissioning pending
2 packages will be comissioned in 15 days
Kamath Bro | Comissioned
UPSO | Md. Aquil, 9415019131 |  |  |  | Akashdeep
10 packages comissioning remaining |  |  | 5820249 |  | Aqil call on Wednesday for PBG format
PSO | Dwarika Prasad, Nigam GM Engg. 9414048039, Shoaib Md. |  |  |  | 1 PBG received and 1 PBG processed
3 Packages |  | 601995 | 9867
2 Running
MPSO | Meher Nosh
1 Pacakge |  | 147000 | 578200 | 107174 | Ammended PO pending from BK
Ammended PO for freight, BG format and amount clearance |  |  |  | Freight charges | Paras sir approval for new PBG
Total |  | 1210312 | 9701116 | 1088832